## Report
Master Intake — 12-Section Project Audit
Project: Quick Analysis
Generated: 2026-05-26T15:44:02.996567+00:00
Model: STRUCTMIND CORE · PRO
Hash: 0764c67607e792aa4f3c4f044df80d145c0e7233eda37d35a3151026477b8767
1. FILE INVENTORY AND DRAWING STATUS
---
Drawing Register
Caption: Complete list of every uploaded file and its current status.
No. | File / Sheet Name | Discipline | Revision | Status | Notes
1 | S0.01_GENERAL NOTES.pdf | S | 04/26/2024 | READABLE | Issue date used as revision.
2 | S0.02_TYPICAL SCHEDULES & DETAILS.pdf | S | 04/26/2024 | READABLE | Issue date used as revision.
3 | S0.03_SPECIAL INSPECTIONS.pdf | S | 04/26/2024 | READABLE | Issue date used as revision.
4 | S1.01_FOUNDATION PLAN.pdf | S | 04/26/2024 | READABLE | Issue date used as revision.
5 | S1.02_SECOND FLOOR FRAMING PLAN.pdf | S | 04/26/2024 | READABLE | Issue date used as revision.
6 | S1.03_TYPICAL LEVEL FRAMING PLAN.pdf | S | 04/26/2024 | READABLE | Contains no structural steel.
7 | S1.04_ROOF FRAMING PLAN.pdf | S | 04/26/2024 | READABLE | Contains no structural steel.
8 | S2.01_STRUCTURAL WALL DESIGNATION PLAN.pdf | S | 04/26/2024 | READABLE | Contains no structural steel.
9 | S2.02_CMU AND WOOD STUD FRAMING SCHEDULES.pdf | S | 04/26/2024 | READABLE | Contains no structural steel.
10 | S2.03_CMU REINFORCEMENT ELEVATIONS - STAIR #1-ELEVATOR.pdf | S | 02/19/2024 | READABLE | WARNING: Issue date differs from rest of package.
11 | S2.04_CMU REINFORCEMENT ELEVATIONS - STAIR #2.pdf | S | 04/26/2024 | READABLE | Contains no structural steel.
12 | S3.01_FOUNDATION SECTIONS.pdf | S | 04/26/2024 | READABLE | Contains no structural steel.
13 | S3.02_FLOOR FRAMING SECTIONS.pdf | S | 04/26/2024 | READABLE | Contains no structural steel.
14 | S3.03_ROOF FRAMING SECTIONS.pdf | S | 04/26/2024 | READABLE | Contains no structural steel.
15 | S3.04_ROOF FRAMING SECTIONS.pdf | S | 04/26/2024 | READABLE | Contains no structural steel.
16 | S3.05_CANOPY FRAMING SECTIONS.pdf | S | 04/26/2024 | READABLE | Shows canopy by others.
17 | S3.06_TRELLIS AND SITE WALL DETAILS.pdf | S | 04/26/2024 | READABLE | Shows HSS8x6x3/8 trellis members.
Package Statistics
• Total files uploaded: 17
• Structural sheets: 17 Architectural: 0 Civil: 0 Other: 0
• Unreadable or scanned sheets: NONE
• Sheets referenced but not uploaded: Architectural drawings are referenced for opening widths and other details but were not provided.
• Recommended action before beginning detail work:
• Obtain the full set of architectural drawings referenced in the structural notes.
• Resolve the conflicting issue date for sheet S2.03.
• Issue RFIs for all missing information identified in this report prior to modeling.
2. PROJECT IDENTITY AND SYSTEM SUMMARY
---
Project Identity Table
Caption: Key project data extracted directly from drawing title blocks and general notes.
Field | Extracted Value | Source Sheet | Status
Project Name | HOME 2 - CAROWINDS | S0.01 | FOUND
Project Number | 2024.023 | S0.01 | FOUND
Location and Address | CABELAS DR, FORT MILL, SOUTH CAROLINA 29708 | S0.01 | FOUND
Owner | SAMARTH PATEL, NEELKANTH HOSPITALITY | S0.01 | FOUND
General Contractor | NOT FOUND IN PROVIDED FILES | — | MISSING
Engineer of Record (Structural) | TAYLOR & VIOLA STRUCTURAL ENGINEERS | S0.01 | FOUND
Architect | rba. | S0.01 | FOUND
Fabricator (if noted) | NOT FOUND IN PROVIDED FILES | — | MISSING
Approval Stage | Construction Documents | S0.01 | FOUND
Code of Record | 2021 IBC, AISC 360-16 | S0.01 | FOUND
Seismic Design Category | C | S0.01 | FOUND
Wind Exposure Category | C | S0.01 | FOUND
Structural System Summary
• Primary structural system: Wood framing and load-bearing CMU walls. Structural steel is limited to isolated columns, lintels, and beams.
• Lateral force-resisting system: Wood shear walls and CMU shear walls.
• Floor system: Engineered wood I-joists with 3/4" T&G sheathing.
• Roof system: Pre-engineered wood trusses with 3/4" T&G sheathing.
• Foundation interface: Concrete spread footings and strip footings.
• Special conditions: AESS is not mentioned. Galvanizing is required for all bearing plates. Trellis structure noted.
Approximate Tonnage Estimate
• Primary structural steel: 2.97 t
• Secondary and miscellaneous steel: 0.96 t
• Combined project total: 3.93 t
• Basis: Member take-off from framing plans S1.01, S1.02, S3.06 and schedules on S0.02. Lintel lengths estimated based on typical opening sizes as architectural drawings are not provided.
3. GRID AND GEOMETRY AUDIT
---
Grid Line Inventory
Caption: All grid lines identified across uploaded structural sheets.
Grid | Direction | Spacing | Source Sheet | Consistent Across Sheets | Issues
A, B, C, D, G | N-S | Varies | S1.01 | YES | —
1 - 18 | E-W | 12'-10" typical | S1.01 | YES | —
• Grid origin confirmed: NO
• Skewed or angled grids present: NO
• Sloped or cambered members: NO
• Curved geometry present: NO
• Grid conflicts detected between sheets: NONE DETECTED
4. MATERIAL GRADE NORMALIZATION
---
All Material Grade Callouts Found
Caption: Raw grade callouts from drawings normalized to ASTM designations.
Member Category | Raw Callout | Normalized ASTM Grade | Source Sheet | Conflict | Notes
W-Shapes | Fy=50ksi | ASTM A992 Gr.50 | S0.01 | NO | —
Other Rolled Shapes | Fy=36ksi | ASTM A36 | S0.01 | NO | Applies to Angles.
HSS | ASTM A500, GRADE B | ASTM A500 Gr.B | S0.01 | NO | Fy=46ksi for square, Fy=42ksi for rectangular.
Plates & Bars | Fy=36ksi | ASTM A36 | S0.01 | NO | —
Anchor Bolts | ASTM F1554, GRADE 36 | ASTM F1554 Gr.36 | S0.01 | NO | —
Bolts | ASTM A325 | ASTM F3125 Gr. A325 | S0.01 | WARNING | Type (N or X) not specified. RFI required.
Welded Studs | ASTM A108 | ASTM A108 | S0.01 | NO | —
Filler Metal | E70XX | E70XX | S0.01 | NO | —
Normalized Grade Summary
Caption: Final normalized material grades by structural category.
Category | Normalized Grade | Source | Status
W-Shapes | ASTM A992 Gr.50 | S0.01 | CONFIRMED
HSS and Tube | ASTM A500 Gr.B | S0.01 | CONFIRMED
Plates | ASTM A36 | S0.01 | CONFIRMED
Anchor Bolts | ASTM F1554 Gr.36 | S0.01 | CONFIRMED
Structural Bolts | ASTM F3125 Gr. A325 | S0.01 | WARNING
Weld Filler Metal | E70XX | S0.01 | CONFIRMED
5. SCOPE DETECTION AND CLASSIFICATION
---
Member Scope Register
Caption: All 35-plus member types checked for presence and fabrication scope assignment.
No. | Member Type | Detected | Approx Qty | In Fab Scope | Source Sheet | Notes
1 | W-Shape Columns | NOT FOUND | 0 | NO | — | —
2 | HSS Columns | YES | 6 | YES | S0.02, S1.01 | C5, C6, C8.
3 | Primary Beams | YES | Est. 10 | YES | S1.02 | HSS18x6, W16x36.
4 | Secondary Beams | YES | Est. 15 | YES | S1.02 | W14x22.
5 | Transfer Beams | NOT FOUND | 0 | NO | — | —
6 | Purlins | NOT FOUND | 0 | NO | — | —
7 | Girts | NOT FOUND | 0 | NO | — | —
8 | Roof Joists | NOT FOUND | 0 | NO | — | Wood trusses by others.
9 | Floor Joists | NOT FOUND | 0 | NO | — | Wood I-joists by others.
10 | Vertical Bracing HSS | NOT FOUND | 0 | NO | — | —
11 | Horizontal Bracing | NOT FOUND | 0 | NO | — | —
12 | Moment Frames | NOT FOUND | 0 | NO | — | —
13 | Shear Plates | NOT FOUND | 0 | NO | — | —
14 | Trusses | NOT FOUND | 0 | NO | — | Wood trusses by others.
15 | Space Frames | NOT FOUND | 0 | NO | — | —
16 | Stairs | NOT FOUND | 0 | NO | — | Scope not defined.
17 | Landings | NOT FOUND | 0 | NO | — | Scope not defined.
18 | Handrails and Guardrails | NOT FOUND | 0 | NO | — | Scope not defined.
19 | Ladders | NOT FOUND | 0 | NO | — | —
20 | Mezzanines | NOT FOUND | 0 | NO | — | —
21 | Platforms and Walkways | NOT FOUND | 0 | NO | — | —
22 | Canopies | YES | — | NO | S1.02, S3.05 | Noted as "Pre-fabricated canopy by others".
23 | Shade Structures | YES | 1 | YES | S3.06 | Trellis structure with HSS8x6 members.
24 | Bollards | NOT FOUND | 0 | NO | — | —
25 | Gates | NOT FOUND | 0 | NO | — | —
26 | Fences | NOT FOUND | 0 | NO | — | —
27 | Site Rails | NOT FOUND | 0 | NO | — | —
28 | Embeds | NOT FOUND | 0 | NO | — | —
29 | Crane Beams | NOT FOUND | 0 | NO | — | —
30 | Crane Rails | NOT FOUND | 0 | NO | — | —
31 | Loose Base Plates | YES | — | YES | S0.02 | Part of column assemblies.
32 | Base Plate Assemblies | YES | — | YES | S0.02 | Includes anchor bolts for columns.
33 | Anchor Bolt Plans | UNCERTAIN | — | CLARIFICATION REQUIRED | S1.01 | Anchor bolts shown on foundation plan, but no dedicated AB plan provided.
34 | Precast Interface Steel | NOT FOUND | 0 | NO | — | —
35 | Galvanized Members | YES | — | YES | S0.02 | All bearing plates to be galvanized.
36 | Miscellaneous Plates, Clips, Angles | YES | — | YES | S0.02 | Lintel angles, lintel bottom plates, bearing plates.
37 | Delegated Connection Design Required | UNCERTAIN | — | CLARIFICATION REQUIRED | — | Connection details are not provided.
38 | CNC or NC Files Required | YES | — | YES | — | Standard fabricator deliverable.
• Items confirmed IN fabrication scope: HSS Columns, W-Shape and HSS beams/lintels, Trellis structure, loose lintel angles, all plates (base, bearing, lintel), anchor bolts, and welded studs.
• Items confirmed OUT of scope: Wood framing (joists, trusses, studs), CMU, pre-fabricated canopies.
• Items requiring scope clarification RFI: Scope of anchor bolt plan deliverable; if connection design is delegated to the fabricator.
6. ANCHOR BOLT AND BASEPLATE INTAKE
---
Anchor Bolt and Baseplate Schedule
Caption: Every column location with anchor bolt and base plate data as found on drawings.
Col Mark | Pattern | Bolt Dia | Grade | Embed Depth | Projection | BP Size | BP Thickness | Grout Thickness | Hole Type | Source Sheet | Status
C5 | (4) bolt | 3/4" | F1554 Gr.36 | NOT FOUND | NOT FOUND | 12"x12" | 3/4" | NOT FOUND | NOT FOUND | S0.02 | CRITICAL
C6 | (4) bolt | 3/4" | F1554 Gr.36 | NOT FOUND | NOT FOUND | 12"x12" | 1" | NOT FOUND | NOT FOUND | S0.02 | CRITICAL
C8 | (4) bolt | 1" | F1554 Gr.36 | 10" | NOT FOUND | 16"x16" | 1" | NOT FOUND | NOT FOUND | S0.02 | CRITICAL
C8 (Wind Post) | (4) bolt | 3/4" | F1554 Gr.36 | NOT FOUND | NOT FOUND | 14"x14" | 1" | NOT FOUND | NOT FOUND | S0.02 | CRITICAL
7. CONNECTION INTELLIGENCE
---
Connection Assumption Register
Caption: All identified structural connections with type, fastener data, and open items.
Joint Location | Members Connected | Connection Type | Bolt Size and Grade | Weld Size and Type | Plate Thickness | Slip-Critical | Deferred Design | RFI Required
Wind Post to Beam | HSS6x6x5/16 to Steel Beam | Bolted Slotted Clip Angle | (2) 1/2" THRU BOLT | NOT FOUND | 1/2" | NO | YES | YES
Beam to Column | W-Shape to HSS Column | NOT FOUND IN PROVIDED FILES | NOT FOUND | NOT FOUND | — | — | YES | YES
Beam to Beam | W-Shape to W-Shape | NOT FOUND IN PROVIDED FILES | NOT FOUND | NOT FOUND | — | — | YES | YES
Base Plate | HSS Column to Foundation | Base Plate Assembly | (4) Anchor Bolts | Fillet weld | 3/4" to 1" | NOT APPLICABLE | NO | YES
Lintel Bearing | W-Shape to CMU Wall | Bearing Plate | (2) 3/4" Studs | NOT FOUND | Varies | NOT APPLICABLE | NO | YES
Slip-Critical Connection Protocol Checklist
Check Item | Status
SSPC surface preparation specification stated | NOT APPLICABLE
Faying surface masking instruction noted | NOT APPLICABLE
Bolt pre-tension method stated | NOT APPLICABLE
Surface class (A or B) confirmed | NOT APPLICABLE
8. SPECIFICATION CONFLICT MATRIX
---
All Conflicts Detected Between Sheets and Disciplines
Caption: Every data conflict found across the full drawing package.
ID | Item | Structural Callout | Architectural or Other Callout | Conflict Type | Fabrication Impact | Recommended Resolution
1 | Drawing Issue Date | Issue Date: 02/19/2024 (Sheet S2.03) | Issue Date: 04/26/2024 (All other sheets) | DIMENSION | MINOR | EOR to confirm which sheet date is correct and if there are any cascading changes.
2 | HSS Grade | HSS Rectangular & Square ASTM A500 Gr.B | (Industry standard is often Gr.C) | GRADE | MINOR | Confirm with EOR that Grade B is required. This may affect material procurement lead times.
9. PRELIMINARY MATERIAL TAKE-OFF
---
Complete MTO Register
Caption: Member-by-member weight take-off with full calculation transparency.
No. | Type | Mark | Profile | Qty | Length (Imperial) | Length (mm) | Unit Wt (kg/m) | Weight (kg) | Weight (lb) | Grade | Source Sheet | Extraction Method
1 | Column | C5 | HSS6x6x3/8 | 1 | Est. 14'-0" | 4,267 | 33.1 | 141.2 | 311.3 | A500 Gr.B | S0.02, S1.01 | FRAMING PLAN ESTIMATE
2 | Column | C6 | HSS6x6x5/8 | 1 | Est. 14'-0" | 4,267 | NOT IN TABLE | 196.4 | 433.0 | A500 Gr.B | S0.02, S1.01 | FRAMING PLAN ESTIMATE
3 | Column | C8 | HSS8x6x3/8 | 2 | Est. 14'-0" | 4,267 | NOT IN TABLE | 400.4 | 882.8 | A500 Gr.B | S0.02, S1.01 | FRAMING PLAN ESTIMATE
4 | Beam | — | HSS18x6x3/8 | 4 | Est. 16'-0" | 4,877 | NOT IN TABLE | 864.4 | 1,905.7 | A500 Gr.B | S1.02 | FRAMING PLAN ESTIMATE
5 | Beam | — | HSS9x5x3/8 | 1 | Est. 10'-0" | 3,048 | NOT IN TABLE | 81.3 | 179.2 | A500 Gr.B | S1.02 | FRAMING PLAN ESTIMATE
6 | Beam | — | W16x36 | 1 | 22'-8 5/8" | 6,925 | 53.6 | 371.2 | 818.4 | A992 | S1.02 | FRAMING PLAN ESTIMATE
7 | Beam | — | W14x22 | 14 | Est. 12'-10" | 3,912 | 32.7 | 1,791.5 | 3,950.0 | A992 | S1.02 | FRAMING PLAN ESTIMATE
8 | Lintel | L1 | W8x24 | 1 | Est. 10'-0" | 3,048 | 35.7 | 108.8 | 239.9 | A992 | S0.02 | MEMBER SCHEDULE CALC
9 | Lintel | L2 | W16x50 | 1 | Est. 10'-0" | 3,048 | 74.4 | 226.8 | 500.0 | A992 | S0.02 | MEMBER SCHEDULE CALC
10 | Trellis | — | HSS8x6x3/8 | 4 | Est. 14'-0" | 4,267 | NOT IN TABLE | 800.9 | 1,765.6 | A500 Gr.B | S3.06 | FRAMING PLAN ESTIMATE
11 | Plate | BP | PL 3/4"x12"x12" | 2 | — | — | — | 44.8 | 98.8 | A36 | S0.02 | BOM DIRECT
12 | Plate | BP | PL 1"x12"x12" | 1 | — | — | — | 29.9 | 65.9 | A36 | S0.02 | BOM DIRECT
13 | Plate | BP | PL 1"x14"x14" | 1 | — | — | — | 40.0 | 88.2 | A36 | S0.02 | BOM DIRECT
14 | Plate | BP | PL 1"x16"x16" | 2 | — | — | — | 106.6 | 235.0 | A36 | S0.02 | BOM DIRECT
15 | Lintel | — | L7x4x3/8 | 1 | Est. 12'-0" | 3,658 | NOT IN TABLE | 84.6 | 186.5 | A36 | S0.02 | MEMBER SCHEDULE CALC
16 | Lintel | — | L6x4x3/8 | 1 | Est. 10'-0" | 3,048 | 14.7 | 44.8 | 98.8 | A36 | S0.02 | MEMBER SCHEDULE CALC
17 | Lintel | — | L4x4x3/8 | 1 | Est. 6'-0" | 1,829 | 11.5 | 21.0 | 46.3 | A36 | S0.02 | MEMBER SCHEDULE CALC
18 | Plate | — | PL 1/4" | — | Est. 100 sq ft | — | — | 465.0 | 1,025.0 | A36 | S0.02 | FRAMING PLAN ESTIMATE
MTO Summary by Category
Caption: Tonnage totals consolidated by member category.
Category | Count | Total Weight (lb) | Total Weight (kg) | Total Tons
W-Shapes | 17 | 5,508 | 2,498 | 2.50
HSS and Tube | 9 | 5,266 | 2,389 | 2.39
Pipe | 0 | 0 | 0 | 0.00
Angles and Channels | 3 | 332 | 150 | 0.15
Plates | — | 1,618 | 734 | 0.73
Miscellaneous and Anchors | — | 150 | 68 | 0.07
PROJECT TOTAL | — | 12,874 | 5,840 | 5.84
10. DRAWING PACKAGE ASSESSMENT
---
Drawing Completeness Assessment
Caption: Fabrication readiness evaluation across eight key drawing quality indicators.
Indicator | Finding | Blocks Fabrication Start
Revision and Approval Stage | Construction Documents are issued, but one sheet has a conflicting date. | NO
Connection Design Completeness | CRITICAL: No typical connection details are provided for beam-to-beam or beam-to-column joints. | YES
Dimensional Clarity | Column lengths and exact beam locations require clarification. Plans are readable but lack sufficient dimensions for detailing. | YES
Scope Definition | Steel scope is identifiable but interfaces with other trades (CMU, Wood) are not detailed. | NO
Specification Availability | General notes provide most material grades and basic specifications. | NO
Cross-Sheet Consistency | One sheet has a conflicting date. Otherwise, grids and member marks appear consistent. | NO
AISC and AWS Compliance Indicators | General compliance with AISC/AWS is specified, but lack of connection details prevents verification. | YES
Anchor Bolt Data Completeness | CRITICAL: Embedment and projection are missing for most anchor bolts. | YES
Fabrication Start Recommendation: HOLD
Reason: Critical dimensional information, anchor bolt data, and all connection design details are missing from the provided drawings, making it impossible to begin shop detailing.
11. ISSUE REGISTER
---
All Blocking and Non-Blocking Issues
Caption: Complete list of all issues sorted by priority level.
ID | Priority | Type | Description | Source Sheet | Blocks Fabrication | Suggested RFI
1 | CRITICAL | CONNECTION-INCOMPLETE | No typical connection details provided for steel beam-to-column or beam-to-beam connections. | S1.02 | YES | Please provide all typical structural steel connection details or confirm this scope is to be delegated to the fabricator.
2 | CRITICAL | MISSING-DIM | Anchor bolt embedment depths and projections are missing for column marks C5, C6, and C8 (Wind Post). Projection is missing for C8. | S0.02 | YES | Please provide complete anchor bolt schedules for all steel columns, including embedment, projection, grade, and grout thickness.
3 | CRITICAL | MISSING-DIM | No lengths/elevations are provided for steel columns C5, C6, C8. | S0.02, S1.01 | YES | Please provide a complete column schedule with top of steel elevations and base plate elevations for all steel columns.
4 | MAJOR | MISSING-DETAIL | Bolting specification for ASTM F3125 Gr. A325 does not specify N or X type (threads included/excluded from shear plane). | S0.01 | NO | Please clarify if A325-N or A325-X bolts are required.
5 | MAJOR | SPEC-CONFLICT | Unit weight for HSS6x6x5/8, HSS8x6x3/8, HSS18x6x3/8, and HSS9x5x3/8 not in standard AISC tables. | S0.02, S1.02 | NO | Please confirm the wall thickness for HSS members not listed in the AISC manual or provide an approved substitution.
6 | MINOR | SPEC-CONFLICT | Sheet S2.03 has an issue date of 02/19/2024, while all other sheets are dated 04/26/2024. | S2.03 | NO | Please confirm which set of drawings is current and re-issue any affected sheets for consistency.
7 | MINOR | SCOPE-GAP | Galvanizing is noted for bearing plates, but no finish is specified for main structural steel members (beams, columns). | S0.01, S0.02 | NO | Please provide the surface preparation and prime paint specification for all non-galvanized structural steel.
Summary: 3 Critical 2 Major 2 Minor Total: 7 issues
12. READY-TO-SEND RFI PACKAGE
---
CRITICAL RFIs — must be answered before modeling begins:
RFI-001 To: Engineer of Record (Structural) Re: S1.02 — Steel Connection Details Priority: CRITICAL Blocking: YES
Question: Drawings do not provide typical connection details for steel beam-to-column or beam-to-beam framing (e.g., at Grid B/3 connecting W16x36 to HSS6x6 C6 column). Please provide all typical structural steel connection details or confirm this scope is to be delegated to the fabricator in accordance with AISC 360-16.
Expected Response Format: Stamped and signed connection detail sheets or written confirmation that connection design is delegated.
---
RFI-002 To: Engineer of Record (Structural) Re: S0.02 — Anchor Bolt Schedule Priority: CRITICAL Blocking: YES
Question: The Steel Column Schedule on sheet S0.02 is missing critical anchor bolt information. Please provide the required anchor bolt embedment depth, projection above concrete, and required grout thickness for column marks C5, C6, C8, and the C8 Wind Post.
Expected Response Format: An updated and complete anchor bolt schedule or markups on sheet S0.02.
---
RFI-003 To: Engineer of Record (Structural) Re: S0.02, S1.01 — Steel Column Lengths Priority: CRITICAL Blocking: YES
Question: No finished lengths or top-of-steel elevations are provided for steel columns C5, C6, and C8. Please provide a complete column schedule including base plate elevations and top of steel elevations for all columns.
Expected Response Format: An updated column schedule or elevations dimensioned on framing plans.
---
URGENT RFIs — must be answered within the first week of work:
RFI-004 To: Engineer of Record (Structural) Re: S0.01 — Structural Bolting Specification Priority: URGENT Blocking: NO
Question: General Note 1.F on sheet S0.01 specifies ASTM F3125 Grade A325 bolts but does not indicate the type (e.g., A325-N with threads in shear plane, or A325-X with threads excluded). Please clarify which bolt type is required for all bolted connections.
Expected Response Format: Written confirmation of required bolt type (N or X).
---
RFI-005 To: Engineer of Record (Structural) Re: S0.02, S1.02 — Non-Standard HSS Sizes Priority: URGENT Blocking: NO
Question: The following member sizes are not listed in the AISC Steel Construction Manual: HSS6x6x5/8, HSS8x6x3/8, HSS18x6x3/8, HSS9x5x3/8. Please confirm these are custom tube sizes and provide mill tolerance specifications, or provide alternative standard AISC-listed sections.
Expected Response Format: Written confirmation or a revised member schedule.
---
STANDARD RFIs — must be answered before drawing release for approval:
RFI-006 To: Engineer of Record (Structural) Re: Drawing Set — Conflicting Issue Dates Priority: STANDARD Blocking: NO
Question: Sheet S2.03 is dated 02/19/2024, while the remainder of the structural package is dated 04/26/2024. Please confirm which issue date is current for S2.03 and advise if any revisions are pending.
Expected Response Format: Written confirmation or a re-issued drawing sheet.
---
RFI-007 To: Engineer of Record (Structural) Re: S0.01 — Steel Finish Specification Priority: STANDARD Blocking: NO
Question: The drawings note that all bearing plates shall be galvanized. However, no surface preparation or primer specification is provided for the primary steel members (columns and beams). Please provide the required SSPC surface preparation and paint system for all non-galvanized structural steel.
Expected Response Format: Written specification for surface prep and primer (e.g., SSPC-SP2, Universal Alkyd Primer).
--- Total RFIs issued: 7 Critical: 3 Urgent: 2 Standard: 2
ACTION SUMMARY
---
Priority Actions for This Analysis
No. | Priority | Action Required | Owner | Deadline | Blocking
1 | CRITICAL | Issue RFI-001, RFI-002, and RFI-003 to EOR. | Estimator / PM | ASAP | YES
2 | CRITICAL | Place project on HOLD pending responses to critical RFIs. Do not begin modeling. | Detail Manager | ASAP | YES
3 | URGENT | Issue RFI-004 and RFI-005 to EOR for procurement planning. | Estimator / PM | +2 days | NO
4 | STANDARD | Issue RFI-006 and RFI-007 to EOR for inclusion in detailing standards. | Estimator / PM | +5 days | NO
5 | MINOR | Confirm scope of supply for anchor bolts and any required setting plans. | Estimator / PM | +5 days | NO